Cross Country                                  	TO DO LIST FOR HOME XC MEET

Get information letter out to schools (ASPI MEET link) (August 1st)

AD creates the link

Secretary needs to update the letter and send to designated schools

3-4 Days prior to meet entries must be entered online

Assign workers (Week prior)

Back Up Timers –

Reader –

Writer-

Chute- 5

Medals –

Parking –

Gators – 3

Line up EMT – t (First week of August)

Line up Trainer – Jenny Edmundson (First week of August)

Find starter – Mike Hale (End of current Fall Season)

Line up Gators – 3-4 (A & M Green Power, School, Other people)

Coordinate concession stand – Booster Club (First week of August)

Verify School Contracts (First week of August, prior to letter)

Work with coaches on course/ creating maps – Secretary needs to verify this was done with print shop (First week of August)

Equipment check (timers and laptops) – (IT department) (First week of August)

Sound System check –(Gordon 402-250-7281) checked and borrowed equipment from Mark Ford) (First week of August)

Power-PA- Check with amphitheater for power and PA for senior night

Ribbons – Order from Trophies Plus (800-397-9993) (After the event)

Medals– Order from Trophies Plus (800-397-9993) (After the event)

Order Flowers (1 extra) – Order from Buttercup Floral (week before)

Check with Coaches about who are the seniors and who needs to be recognized (2 weeks prior)

Order BIB numbers – Rainbow Racing (After the event)

Inform Stake holders of date (First Week of August)

Lake park – Ron Maddox 520-7275

Police - anyone

IT Department

Booster Club

Parents

Line up porta-potties 5 total – Linkon Logs (Call Clay Lincoln/Frank) (First Week of August)

Put names on the BIB numbers – ongoing as soon as entries are in

Need two people at entrance for parking for big meets

Move bleachers to finish line for spectators

Mike Hale-Early August

Equipment

| 1. 2 reems of paper 2. Markers 4. Staplers- paper clips- tape 5. Clip boards – 2/3 7. 2 tables 8. Chair 9. Folders (start and finish) 10. Envelopes 11. Extra numbers and safety pins 12. 2 Gators & 1 Medical Gator 13. Hand sanitizer 15. Tent 17. Timer System 18. Stop Watches 19. Excel Sheet for finish line 6 20. Walkies 21. Flowers 22. 2 Ten Gallon Water Coolers and Gatorade 23. Statement of Claim form for starter 24. Extension cord and power strip |  |
| --- | --- |

8	Cones for Finish Line

3-4	Gators with Gas

1	Tent

2	Cases of Gatorade

Medals/Ribbons

2	Tables

3	Chairs

6	Walkies